Intake & Payments System for Waghi Valley Produce Cooperative

Task 2: Requirements Specification & Delivery Estimate

Name: Shanty Lakapua
Course: CMN224
Date: 27/09/2026

Part 1 — Concise Software Requirements Specification

1.1 Purpose & Scope

Waghi Valley Produce Cooperative (WHP) is a 300-member cooperative in the Western Highlands. Members bring coffee and vegetables to a roadside depot, where a clerk weighs and records the produce in carbon-copy books. The co-op pays members fortnightly. The problem the manager keeps raising is simple: records go missing. Books get lost, pages tear, and when a member says, "you didn't pay me for that sack of coffee," there's no second copy to prove otherwise. Disputes are constant, and the member committee is losing patience.

This report specifies a desktop application that runs at the depot and at the town office. It records every intake (what came in, from whom, how much, at what price), tracks what's owed to each member, generates a numbered payment slip for every fortnightly payout, and produces a running ledger each member can check. The goal is to make the record disputable-proof — if a member queries a payment, the clerk can pull up the exact entry in under a minute.

In scope:

- Member register (name, village, phone, membership number)

- Intake recording (produce type, weight, grade, price per kg, member)

- Fortnightly payment calculation and batch processing

- Payment slip generation (numbered, printable)

- Per-member ledger (running balance, last 12 months)

- Dispute query: pull up any intake or payment by date range or member

- Daily summary for the depot clerk

- Fortnightly payment summary for the treasurer and committee

- Local storage with USB backup

- Two-person approval for any payment batch before it's finalised

Out of scope (v1):

- Mobile app or tablet client for the depot

- SMS or phone-based member notification

- Live bank or mobile-money API integration

- Multi-depot or multi-cooperative support

- Agricultural advisory features (crop pricing, market data)

- Member voting or committee meeting management

- Anything requiring a continuous internet connection at the depot.

- Payroll for the co-op's own staff (clerk, manager, treasurer)

- Inventory management for stored produce (beyond the intake record)

These are excluded because the depot has no mains power, no fixed internet, and patchy mobile signal. The town office is 20 minutes away and is the only place with reliable 4G. Anything that needs a connection at the depot is out. Anything that needs a second device is out. The system has to work on one laptop, offline, in the conditions the depot actually has.

1.2 Business Context & Stakeholders

WHP is a member-owned cooperative. That means the members are both the customers (they bring produce in) and the shareholders (they vote on how the co-op runs). The member committee has explicit authority: any change that affects payments needs their approval. That's not a suggestion it's written into the co-op's constitution. So, the system can't just be "installed and used." The committee has to see it, understand it, and sign off before it goes live.

The depot is a roadside location. It's not an office. It's a shed with a scale, a table, and a laptop. The clerk works there alone most of the day. The manager visits a few times a week. The treasurer and committee meet at the town office, which is 20 minutes away by road.

| Stakeholder | Role in system | Primary need | Influence on project |
| --- | --- | --- | --- |
| Depot clerk | Main user. Records every intake, prepares payment batches. | Fast entry (produce comes in continuously); simple screens; no training beyond 20 min; system must work offline. | High — she's at the depot every day. If the system is slower than the carbon-copy book, she'll go back to the book. Her daily workflow is the whole point. |
| Manager | Visits depot a few times a week. Reviews daily summary. Approves payment batches (first of two signatures). | See what came in each day; flag anomalies (e.g., a member's weight is 3× their usual); approve or reject a payment batch before it goes to the treasurer. | High — co-signs every payment batch. If he doesn't trust the numbers, payments don't go out. |
| Treasurer | Works from the town office. Processes the actual cash/mobile-money payouts. Reconciles the batch against the cash out the door. | A clean, numbered payment list per member per fortnight; a batch total that matches the cash prepared; a running member balance so he can answer "what do I owe this member?" without digging through books. | High — if the numbers don't reconcile, he won't sign. He's the last gate before money moves. |
| Member committee (5–7 people) | Approves any change affecting payments. Reviews the fortnightly summary. Mediates disputes. | A summary they can read in 5 minutes: total paid, total outstanding, top disputes. Access to any member's ledger if a dispute comes up. | High (gate) — they must sign off on the system before go-live. They also must approve any future change to how payments work. Without their sign-off, the project stalls. |
| Members (300) | Bring produce in; receive fortnightly payments. Query their own balance. | A payment slip with a number they can quote. The ability to ask "what did you weigh my coffee at?" and get an answer fast. | Medium (collective) — no single member has veto power, but if a large group feels the system is unfair or opaque, the committee will pull support. Their trust is the product. |
| Co-op accountant (external, part-time) | Monthly reconciliation. Annual report. | Exportable data (CSV or print) for the monthly books. A clean audit trails. | Low (intermittent) — comes in once a month. Needs the data, not the system. |

The clerk and the treasurer are the two people who touch the system every single day (clerk) or every fortnight (treasurer). If either of them finds it confusing, the system dies. The committee is the political gate, they don't use it daily, but they have to believe in it.

1.3 Functional Requirements

Each one is a single, testable shall-statement. MoSCoW: Must = can't run without it; Should = important, workaround exists; Could = nice if time allows; Won't = deferred past v1.

| ID | Requirement | Priority |
| --- | --- | --- |
| FR-1a | The system shall allow the clerk to select a member from the register as the supplier of an intake. | Must |
| FR-1b | The system shall record the produce type (coffee, vegetable, or other) for each intake. | Must |
| FR-1c | The system shall record the weight (in kg) of each intake. | Must |
| FR-1d | The system shall record the grade or quality classification of the produce (e.g., coffee Grade A, Grade B; vegetable: fresh, damaged). | Must |
| FR-1e | The system shall record the price per kg applied to the intake, defaulting to the current co-op price schedule. | Must |
| FR-1f | The system shall calculate the total amount owed for the intake (weight × price per kg) and display it to the clerk before confirmation. | Must |
| FR-1g | The system shall record the date of the intake, defaulting to the current date. | Must |
| FR-2 | The system shall assign a unique, sequential, non-reusable intake slip number to every recorded intake. | Must |
| FR-3 | The system shall assign a unique, sequential, non-reusable payment slip number to every payment made to a member. | Must |
| FR-4 | The system shall calculate each member's running balance (total intakes minus total payments) and display it on request. | Must |
| FR-5 | The system shall generate a printable intake slip showing slip number, member name, produce type, weight, grade, price per kg, total amount, date. | Must |
| FR-6 | The system shall generate a printable payment slip showing payment slip number, member name, amount paid, payment method (cash / mobile money), date, and the member's remaining balance after payment. | Must |
| FR-7 | The system shall allow the clerk to prepare a fortnightly payment batch: a list of all members with a positive balance, the amount owed to each, and the batch total. | Must |
| FR-8 | The system shall require two approvals (manager AND treasurer) before a payment batch is marked as "finalised" and the individual payment slips are generated. | Must |
| FR-9 | The system shall maintain a member register: full name, village, phone number, membership number, date of joining. | Must |
| FR-10 | The system shall allow the clerk to record a daily summary at the end of the working day: total kg received, total amount owed, number of members served, and any anomalies noted. | Must |
| FR-11 | The system shall allow the treasurer to record the actual payment method (cash or mobile money) and, for mobile money, the transaction reference number, for each payment in a batch. | Must |
| FR-12 | The system shall allow any user to look up a member's full ledger: all intakes and all payments, in date order, for a selectable period (default: last 12 months). | Must |
| FR-13 | The system shall allow the clerk to edit the co-op price schedule (price per kg per produce type per grade) effective from a given date. Past intakes shall not be affected by a price change. | Must |
| FR-14 | The system shall export a fortnightly payment summary (total paid, number of members paid, total outstanding, top 5 largest balances) in a print-friendly format for the committee. | Should |
| FR-15 | The system shall allow the clerk to search for a member by name, village, or membership number. | Should |
| FR-16 | The system shall allow the manager to flag an intake as "disputed" with a reason, which locks the entry from being included in the next payment batch until resolved. | Should |
| FR-17 | The system shall allow the treasurer to void a payment slip (mark as cancelled) with a mandatory reason; the number is never reused. | Should |
| FR-18 | The system shall allow the clerk to record a deduction (e.g., for damaged produce, transport cost) against a member's intake, with a reason. | Should |
| FR-19 | The system shall generate a monthly reconciliation report: total intakes by type, total payments by method, opening and closing balances per member. | Could |
| FR-20 | The system shall display a simple dashboard on launch: today's total kg received, total amount owed today, number of members with a balance over K500. | Could |
| FR-21 | The system shall send an SMS to a member's phone when their payment has been processed. | Won't (v1) |
| FR-22 | The system shall integrate with a mobile-money API to process payments automatically. | Won't (v1) |
| FR-23 | The system shall support a member-facing portal or USSD code for balance checking. | Won't (v1) |

Why the Must set looks like this: The board's (committee's) stated problem is that records go missing, and disputes follow. The Must set is built around making the record unmissable and the payment verifiable. FR-2 and FR-3 (unique, non-reusable numbers) mean every intake and every payment has an identity. FR-12 (member ledger) means a member can see their own history. FR-8 (two-person approval) means no single person can move money without a check. FR-11 (transaction reference for mobile money) means the treasurer can prove the money actually left the account. Without these, you've just digitised the carbon-copy book — same risk, new format.

1.4 Non-Functional Requirements

Each one is measurable and tied to a specific condition at the depot or the town office.

| ID | Requirement | Measure | Why it matters here |
| --- | --- | --- | --- |
| NFR-1 | Operation on solar-charged battery. The system shall run for a minimum of 6 continuous hours on the laptop's battery (charged from the depot's solar panel) without mains power. | Measured: laptop runs the system for 6 hours on a full solar charge with the screen at 50% brightness. | The depot has no mains power. Solar is the primary source; the generator is backup. A 6-hour window covers a full working day at the depot (typically 7 am – 1 pm, with a break). |
| NFR-2 | Fully offline at the depot. All Must-priority functions shall work with zero internet connectivity. No sync, no cloud, no network call. | 100% of Must FRs pass with the laptop in airplane mode. | The depot has patchy mobile signal and no fixed internet. The system cannot depend on a connection. The town office (20 min away) has 4G, but the depot does not. |
| NFR-3 | Single-laptop operation at the depot. The system shall run on the existing depot laptop (Windows 10, 4 GB RAM, 256 GB SSD) with no second device, no server, no external storage beyond a USB stick for backup. | Installs and runs on the existing depot laptop. | There is one laptop at the depot. No budget for a second one. |
| NFR-4 | Intake entry speed. From selecting a member to printing the intake slip, the system shall complete the transaction in under 4 seconds. | Measured on the depot laptop with 300 members and 2 years of intake history loaded. | Produce arrives continuously. If the clerk takes 10 seconds per entry, a queue builds. The carbon-copy book takes about 3 seconds (write, tear off, hand over). The system must match or beat that. |
| NFR-5 | Ledger lookup speed. A member's full 12-month ledger shall render in under 3 seconds. | Measured on the depot laptop. | When a member queries their balance (and they will, that's the whole point), the clerk needs to show them the answer before the conversation turns into an argument. 3 seconds is the difference between "here's your record" and "let me go check." |
| NFR-6 | Time to competence. A new depot clerk shall record an intake correctly (all fields, correct member, correct weight) after 20 minutes of training. | Observed during UAT with a new clerk. | Clerks can and do leave. The co-op can't afford a 2-week onboarding. 20 minutes is the ceiling. |
| NFR-7 | Audit integrity. Intake slip numbers and payment slip numbers shall be sequential, unique, and immutable. A voided slip retains its number (marked "VOID") and is never reissued. All edits, voids, and dispute flags are logged with user, timestamp, and reason. | 0 duplicate numbers in a 12-month simulated run; 100% of edits logged. | This is the core of the "trustworthy record" requirement. If a member can't verify that their intake was recorded, the system hasn't solved the problem. |
| NFR-8 | Backup. A one-click "Backup" action copies the full database to a USB drive. The clerk is prompted to back up at the end of each working day. The treasurer performs a second backup at the town office every fortnight (when the payment batch is processed). | Backup restores to a clean machine and reproduces all records. | The depot has no mains power. A generator failure or a solar panel issue means the laptop could die mid-session with no UPS. A daily USB backup at the depot plus a fortnightly backup at the town office (where there's power) gives two independent copies. |
| NFR-9 | Print compatibility. Intake slips and payment slips shall print correctly on the existing depot printer (thermal receipt printer, 58 mm roll) without additional drivers. The fortnightly summary shall print on A4 at the town office. | Verified on the actual depot printer and the town office printer during UAT. | The clerk hands a physical slip to the member at the point of intake. If it doesn't print, the member walks away with no proof. |
| NFR-10 | Data retention. The system shall retain at least 5 years of intake and payment history without performance degradation. | Ledger lookup still under 3 s with 5 years of data (~300 members × 26 fortnights × 5 years ≈ 39,000 payment records; ~300 members × 5 intakes/fortnight × 26 × 5 ≈ 195,000 intake records). | The committee may need historical data for disputes that surface months later, or for the annual report. |
| NFR-11 | Low power consumption. The system shall not cause the laptop battery to drain faster than the baseline Windows idle + browser rate (i.e., the system itself shall add less than 5% to the laptop's power draw). | Measured: battery drain rate with the system running vs. idle. | The laptop is solar-charged. Every extra watt of draw is a minute less of uptime. The system must be lightweight. |

1.5 Constraints & Business Rules

Environmental constraints (facts about the delivery site):

- The depot has no mains power. Power comes from a solar panel (primary) and a small generator (backup). The laptop is charged from the solar system overnight.

- The depot has no fixed internet. Mobile signal is patchy (1–2 bars, intermittent). The system must not depend on it.

- The town office is 20 minutes from the depot by road. It has mains power and 4G. The treasurer works from here.

- One laptop at the depot (Windows 10, 4 GB RAM, 256 GB SSD). One thermal receipt printer (58 mm). One USB stick for backup.

- One laptop at the town office (Windows 10, 8 GB RAM). One A4 printer. 4G connection.

- No dedicated IT staff at either location. The clerk is the de facto system administrator at the depot. The treasurer is the de facto administrator at the town office.

- The co-op operates on a fortnightly payment cycle. Intakes happen daily (Monday to Saturday). Payments are processed every second Saturday.

Business rules (co-op policies the system must enforce):

- The member committee must approve any change that affects payments. This includes: changing the price schedule, changing the payment cycle, adding or removing a deduction type, changing who can approve a batch. The system must log these changes and require a "committee approval" flag (in v1, this is a password or a manual sign-off recorded by the treasurer) before the change takes effect.

- Two-person approval for payment batches. No payment batch is finalised until both the manager and the treasurer have approved it (FR-8). This is non-negotiable per the co-op constitution.

- Price schedule is set by the committee, not the clerk. The clerk can enter the current prices (FR-13) but cannot change them mid-fortnight. A price change takes effect from the next fortnight and requires the committee approval flag.

- Intake slips are issued at the point of delivery. A member who drops off produce expects a slip before they leave. No batching, no "we'll print it later."

- Payment slips show the remaining balance. A member who gets paid K200 but still has K80 owed needs to see that on the slip. This prevents the "you didn't pay me in full" dispute.

- Disputed intakes are locked. Once the manager flags an intake as disputed (FR-16), it is excluded from the next payment batch until the dispute is resolved and the flag is removed by the manager.

- No member record is deleted while they have a non-zero balance. A member who leaves the co-op is marked "inactive" but their balance and history are retained.

- Daily backup at the depot is mandatory. The clerk cannot close the day's session without making a USB backup (NFR-8). The system prompts and does not allow exit until the backup is confirmed.

- Mobile money payments require a transaction reference. The treasurer must enter the reference number from the mobile-money app before the payment is marked complete (FR-11). No reference, no completion. This is the co-op's answer to "did the money actually go through?"

1.6 Glossary

| Term | Plain-language definition |
| --- | --- |
| Intake | One delivery of produce by a member to the depot. E.g., "Member #042 brought 25 kg of Grade A coffee on 14 September." |
| Intake slip | The printed record given to the member at the point of delivery. Shows what was received, at what weight and price, and carries a unique number. |
| Payment slip | The printed record given to the member when they are paid. Shows how much they were paid, how, and what they still have owed. Carries a unique number. |
| Fortnightly payment batch | The list of all members who are owed money at the end of a two-week period, with the amount owed to each. Prepared by the clerk, approved by the manager and treasurer, then processed. |
| Member committee | The elected group (5–7 people) that governs the co-op. They approve changes to payment processes and review the fortnightly summary. |
| Depot | The roadside location where members bring produce. Has a scale, a table, a laptop, a printer, and a solar panel. No mains power. |
| Town office | The co-op's administrative office, 20 minutes from the depot. Has mains power, 4G, and is where the treasurer works. |
| Running balance | A member's current position: total value of all intakes minus total of all payments. A positive number means the co-op owes them money. |
| Dispute flag | A marker the manager puts on an intake when there's a question about the weight, grade, or price. The intake is excluded from payments until the flag is cleared. |
| PGK / Kina | The currency of Papua New Guinea. |

Part 2 — Estimate & Work Schedule

2.1 Task Breakdown

Eight tasks. Each has a named output the client can see and sign off before the next one starts.

| Task | What gets done | Output / deliverable | Depends on |
| --- | --- | --- | --- |
| T1 | Requirements workshop with the clerk, manager, and treasurer. Refine the SRS. Get committee sign-off. | Signed SRS document. Committee approval recorded. | — |
| T2 | Data model and database design. | ERD + SQLite schema (members, intakes, payments, price schedule, disputes, audit log, daily summary). | T1 |
| T3 | UI prototype: intake entry screen + member ledger screen + payment batch screen. | Clickable mockup (Figma or HTML) shown to the clerk and the treasurer. | T2 |
| T4 | Core module: intake recording, intake slip generation, member register, price schedule, daily summary. | Working desktop app with FR-1a–g, FR-2, FR-5, FR-9, FR-10, FR-13. | T3 |
| T5 | Payment module: batch preparation, two-person approval, payment slip generation, member ledger, dispute flag, void, deduction. | Working app with FR-3, FR-4, FR-6, FR-7, FR-8, FR-11, FR-12, FR-16, FR-17, FR-18. | T4 |
| T6 | Resilience pass: battery runtime test (6 hr), offline verification, backup/restore, print layout on the depot thermal printer, low-power check. | Verified NFR-1, NFR-2, NFR-4, NFR-5, NFR-7, NFR-8, NFR-9, NFR-11 on the actual depot laptop and printer. | T5 |
| T7 | UAT with the clerk and the treasurer using real data. Committee review. Defects fixed. | Signed UAT report. Committee approval for go-live. | T6 |
| T8 | Deployment at both locations (depot laptop + town office laptop). Training: clerk (30 min), treasurer (30 min). 2-page user guide. USB backup made at both locations. | System live at the depot and the town office. | T7 |

Assumptions behind the estimate:

- One developer (me), working full-time.

- 5-day working week, 8 hours a day.

- Tech stack: Python 3 + Tkinter + SQLite. Same reason as always: it runs on the existing laptop, needs no runtime the co-op doesn't have, and produces a single executable. I've built a similar desktop Python/SQLite app before (a small inventory tracker, about 6 weeks of work).

- The clerk is available for a 2-hour workshop in Week 2 and a 2-hour UAT session in Week 7.

- The treasurer is available for a 1-hour session in Week 2 and a 1-hour session in Week 7.

- The member committee can be reached for a 30-minute sign-off meeting in Week 2 (T1) and Week 7 (T7). They don't need to be in Port Moresby; a phone call with screen-share from the town office's 4G works.

- No hardware purchases. The depot laptop, printer, and USB stick are already there.

- I have access to the depot for 2 days in Week 6 (resilience pass) and 1 day in Week 7 (deployment). Travel from Port Moresby to the Waghi Valley is about 4 hours by road.

2.2 Time Estimates (PERT)

PERT three-point estimation from the Weeks 5–6 workshop. O = optimistic, M = most likely, P = pessimistic. Formula: Te = (O + 4M + P) / 6.

| Task | O (days) | M (days) | P (days) | Te | Rounded |
| --- | --- | --- | --- | --- | --- |
| T1 – Requirements & committee sign-off | 3 | 4 | 7 | 4.33 | 4 |
| T2 – Data model & DB design | 2 | 3 | 5 | 3.17 | 3 |
| T3 – UI prototype | 3 | 5 | 8 | 5.17 | 5 |
| T4 – Core module (intake) | 5 | 8 | 14 | 8.5 | 9 |
| T5 – Payment module | 5 | 8 | 14 | 8.5 | 9 |
| T6 – Resilience pass (incl. 2 days travel to depot) | 4 | 6 | 10 | 6.33 | 6 |
| T7 – UAT & committee review | 3 | 5 | 10 | 5.5 | 6 |
| T8 – Deployment & training (both locations) | 2 | 3 | 5 | 3.17 | 3 |
| Total |  |  |  | 46.5 | 45 working days |

Total: ~45 working days = 9 weeks. I've added a 15% contingency (7 days) for the risks I can't control: the committee being unavailable for sign-off, the depot laptop having a different Windows version than expected, the thermal printer using a driver I haven't tested, or the road to the Waghi Valley being impassable during the wet season (which is starting). Total with buffer: 52 working days ≈ 10.5 weeks.

Why these numbers and not others:

My baseline is the same as before: a comparable desktop Python/SQLite app took me about 6 weeks. But this project is bigger than that baseline in two ways. First, there are two locations (depot and town office), which means T6 and T8 include travel time I didn't have in a single-site project. I've built that into T6 (6 days instead of 5) and T8 (3 days instead of 2). Second, the payment module (T5) is more complex than the school's reporting module because of the two-person approval workflow, the dispute flag, and the deduction logic. I've set T5's M to 8 (same as T4) rather than 7 because the approval state machine (pending → manager-approved → treasurer-approved → finalised) has more edge cases than a simple report.

For T1, the pessimistic case is 7 days (not 5) because getting the member committee to agree on a meeting time is genuinely hard. They're farmers. They're busy. The committee meets when it meets, and I can't force a schedule. If the first two attempts to set up the sign-off meeting fail, that's 3–4 extra days of back-and-forth.

For T7, the pessimistic case is 10 days because UAT requires the clerk at the depot AND the treasurer at the town office AND the committee available for a review. Coordinating three people across two locations with no reliable internet at the depot means phone calls, WhatsApp voice notes, and possibly a 4-hour drive. If the road is bad (wet season), that drive becomes 6 hours.

The 15% contingency is specifically for: (a) the thermal printer driver not working on the depot laptop's Windows version, (b) the committee needing a second review after the first UAT, and (c) a road closure forcing a reschedule of the depot visit.

2.3 Work Schedule

Start: beginning of Week 2. All delivery complete by end of Week 10. Week 8 is no-contact study week  I've built the schedule so that no critical delivery lands in Week 8, but the resilience pass (T6) and UAT (T7) may spill into it. If that happens, the buffer absorbs it.

| Week | Tasks | Milestone — what the client sees |
| --- | --- | --- |
| Week 2 | T1: Workshop with clerk, manager, treasurer (at the town office, 2 hrs). Refine SRS. Committee sign-off (30-min phone call from town office 4G). T2 begins: data model sketch. | Milestone 1 – SRS signed + committee approval. The clerk, manager, and treasurer each initial the SRS. The committee chair confirms approval by phone (recorded). The treasurer receives a one-page summary of what's being built. |
| Week 3 | T2 completes SQLite schema built, tested with sample data (50 members, 200 intakes). T3 begins: UI prototype. | Milestone 2 – Prototype demo. The clerk and the treasurer see a clickable mockup of the intake entry screen, the member ledger, and the payment batch screen. The clerk confirms the field order matches how she actually works at the scale. The treasurer confirms the batch layout is what he needs to reconcile. |
| Week 4 | T4: Core module build. Intake entry, intake slip generation, member register, price schedule, daily summary. | Milestone 3 – Core demo (mid-week). The clerk records 5 test intakes, prints 5 test intake slips on the thermal printer (I bring a sample 58 mm printer to test the layout). She confirms the workflow feels right and the slip is legible. |
| Week 5 | T4 completes. T5 begins payment batch preparation, two-person approval, payment slip generation, member ledger, dispute flag, void, deduction. | Milestone 4 – Payment demo. The treasurer sees a test payment batch (20 members, ~K8,000 total). He walks through the approval flow: manager approves → treasurer approves → batch finalised → 20 payment slips generated. He confirms the reconciliation view matches what he needs. |
| Week 6 | T5 completes. T6: Resilience pass. Travel to the Waghi Valley (4 hrs). Battery runtime test (6 hrs on solar charge). Offline verification (airplane mode, all Must FRs). Backup/restore test. Print layout on the actual depot thermal printer. Low-power check. | Milestone 5 – Resilience sign-off. The clerk watches the 6-hour battery test. She confirms the system is still running at hour 6. A backup is made to the USB stick and restored to my laptop to verify integrity. The thermal printer prints a test slip correctly. The clerk and treasurer both sign the resilience checklist. |
| Week 7 | T7: UAT. The clerk uses the system with real data: last 3 months of intakes re-entered (~450 records), actual member register (300 members), actual price schedule. The treasurer processes a test payment batch. The committee reviews the fortnightly summary format. Defects fixed. | Milestone 6 – UAT sign-off + committee go-live approval. The clerk and treasurer sign the UAT report. The committee chair confirms go-live approval by phone. Any defects found are fixed before sign-off. |
| Week 8 (no-contact) | T8: Deployment. Travel to the Waghi Valley. Install on the depot laptop. Install on the town office laptop. Train the clerk (30 min) and the treasurer (30 min). Leave a 2-page user guide at each location. Make a final USB backup at both locations. | Milestone 7 – Go-live. The system is running at the depot. The clerk processes 3 real intakes on the first day. The treasurer has the system on his laptop at the town office. Both USB backups are made. |
| Week 9–10 | Buffer. If any defect surfaces in the first week of go-live, fixed by phone/remote instruction (via the town office 4G). No new features. | If a defect is found, it's fixed within 48 hours. The clerk calls the treasurer, the treasurer calls me (phone). No travel unless it's a hardware issue. |

Critical path: T1 → T2 → T3 → T4 → T5 → T6 → T7 → T8. Sequential because there's one developer. The only parallelism is that T2 (data model) can start while T1 (committee sign-off) is still being coordinated, but I've kept them sequential to be safe.

What the client does NOT see: Intermediate code, test logs, or design docs beyond the seven milestones. The clerk is involved at Milestones 1, 2, 3, 5, 6, and 7. The treasurer at 1, 2, 4, 5, 6, and 7. The committee at 1 and 6. The manager at 1, 4, and 6.

Travel note I've built two depot visits into the schedule (Week 6 for the resilience pass, Week 7–8 for deployment). Each visit is a 4-hour drive from Port Moresby (or the nearest town). If the wet season makes the road impassable, I'll do the resilience pass on a similar laptop in Port Moresby and note the limitation in the UAT report. This is a risk, not a plan.

2.4 Dependency-Triangle Analysis

The scope–time–cost triangle. The committee wants the system "before the next payment cycle" but hasn't set a hard date or a budget. I'm offering three options.

|  | Option 1 – Full | Option 2 – Core (recommended) | Option 3 – Minimal |
| --- | --- | --- | --- |
| Scope | All Must + Should + Could (FR-1a through FR-20). Includes monthly reconciliation report, dashboard, deduction logic. | All Must FRs + the three highest-value Should FRs (FR-14 fortnightly summary export, FR-15 member search, FR-16 dispute flag). Defers: FR-17 void, FR-18 deduction, FR-19 reconciliation report, FR-20 dashboard. | Must FRs only. No export, no search beyond membership number, no dispute flag, no void, no deduction. |
| Time | ~12 weeks (60 working days) | ~10.5 weeks (52 working days incl. buffer) | ~7 weeks (35 working days) |
| Effort | 60 days × 8 h = 480 h | 52 days × 8 h = 416 h | 35 days × 8 h = 280 h |
| Risk | High: the Could items (dashboard, reconciliation report) add complexity the clerk won't use daily. The 12-week timeline means go-live is 3 months after start, which is almost a full payment cycle. The co-op runs on carbon-copy books for that entire time, and disputes continue. | Medium: deferred items have workarounds. A void can be handled by entering a negative payment with a note (audit log captures it). A deduction can be handled by adjusting the weight before the intake is saved (clerk enters the net weight). The monthly reconciliation report can be produced by the external accountant from the CSV export of the ledger. Go-live at the start of the next payment cycle. | Low technical risk, high adoption risk: without the dispute flag (FR-16), the manager has no way to lock a questionable intake before the payment batch is prepared. He'll have to call the clerk and say "don't include member #042 in this batch" — which works, but it's a phone call, not a system control. Without member search by name (FR-15), the clerk must know the membership number, which defeats the purpose of a system that's supposed to be easier than the book. |
| What the committee gets at go-live | Everything in the SRS. | Intakes recorded with unique numbers, payments batched with two-person approval, member ledger available, fortnightly summary for the committee, dispute flag for the manager. | Intakes recorded, payments batched, member ledger available. That's it. |

Recommendation: Option 2 (Core).

Here's the reasoning:

- It solves the stated problem. The committee's problem is "records go missing, disputes follow." Option 2 gives every intake and every payment a unique, non-reusable number (FR-2, FR-3). It gives every member a ledger they can check (FR-12). It gives the manager a way to flag a questionable intake before money moves (FR-16). It gives the committee a fortnightly summary they can read in 5 minutes (FR-14). That's the problem, solved.

- It fits the payment cycle. The co-op pays members every second Saturday. If go-live lands at the start of a fortnight, the first payment batch runs through the system. Option 2's 10.5-week timeline means go-live is roughly 2.5 months from start. If we start in early October, go-live is late December — the start of a new payment cycle. Option 1's 12-week timeline pushes go-live to mid-January, which is into a payment cycle, meaning the first batch is done on the old system and the second on the new one. That's a mess for the treasurer.

- The deferred items have real workarounds, not just "we'll do it later." A void: the clerk enters a negative payment with a note, the audit log captures it, the number is unique. It's clunky but it works, and it's rare (maybe 1–2 voids per month). A deduction: the clerk adjusts the weight before saving the intake (e.g., 25 kg gross, 2 kg damaged, enter 23 kg). The intake slip shows the net weight. It's not elegant, but the member sees the number and the price, and the total is correct. The monthly reconciliation report: the external accountant gets a CSV export of the ledger and does the reconciliation in Excel, the same way they do it now. The system makes the data available; it doesn't need to do the accountant's job.

- The buffer is real, not decorative. The 7-day contingency covers the two things most likely to go wrong: the thermal printer driver and the committee's availability. Both are PNG-specific risks that a generic project plan would miss. Option 1 has no buffer; a single printer driver issue pushes it to 13 weeks, which is past the next payment cycle and into a new one.

- The committee's approval structure is respected. Option 2 includes the two-person approval (FR-8) and the committee approval flag for price changes (FR-13 + business rule 1). These are Must items and they're in the core. Option 3 also includes them (they're Must), but Option 3 is too thin to be useful — without the dispute flag and name search, the clerk will go back to the book within a fortnight.

If the committee says "we need the deduction feature and the reconciliation report": add 4 working days (FR-18 is a field on the intake form; FR-19 is a filtered report). Move UAT to the first 3 days of the buffer week. Go-live shifts by one week. That's a scope-for-time trade.

If the clerk says during UAT that the intake entry is too slow (more than 4 seconds): that's a performance issue, not a scope issue. I'll optimise the query or reduce the number of fields on the initial screen. It's a 1–2 day fix, not a schedule change.

If the road to the depot is impassable during the wet season: the resilience pass (T6) is done on a similar laptop in Port Moresby. The UAT (T7) is done at the town office (which has power and 4G). The deployment (T8) happens when the road opens. This adds 1–2 weeks to the timeline but doesn't change the scope or the cost. It's a risk, and it's in the buffer.

References

- Project Management Institute. (2021). A Guide to the Project Management Body of Knowledge (PMBOK Guide), 7th ed.

- Clegg, D. (1995). MoSCoW Prioritisation. Agile Business Consortium.

- Waghi Valley Produce Cooperative. (2025). Client brief: intake & payments system commission. [Internal document].

- Papua New Guinea Institute for Environmental Management. (2023). Solar Power Systems for Rural Applications. PEM.gov.pg.